## Slide 1
Risks / Issues & Mitigation plan | Owner
I: Code Planning & Shift Rotation – T&A required I: Address Fields Mgmt between DF and CGD I: Legal Structure to be adjusted (Defect L1 + Montbrison) I: CEGEDIM waiting for the CR to be signed. 2,5 weeks of delay to test interfaces I: Job Title vs Business Title. Payslip source from Job Title (Support Process) I: Standard Field vs Employee Properties (Validate PT solutions) R: DayForce DM for payslips (Arkevia/PeopleDoc selection process) | Nitin Nitin Véronique Nitin/Chris Anne Ian D. Daniel
Last Period Achievements
Conducted alignment meeting on open issues Confirm Coffre-Fort selection process (criteria / equipiers) Work on detailed PT resource capacity planning Org. Structure update in progress Integrate Nitin’s backup to TMM (Chris) Train Strategy and TMM Rep onboarded.
KPIs | P. Week | Today
COST | Y | Y
SCOPE | R | R
SCHEDULE | R | R
RESOURCES | Y | Y
RISK | R | R
TRANSITION | G | G
Project Weekly Status
[Project Name]
Summary
Cost is Yellow – Change Request Approval In progress Scope is Yellow – Coffre-Fort requirement added to the scope. Selection process in progress Schedule is Red - Go-live December 2st. (To go back to green after CR approved) Risks are Red– If CEGEDIM doesn’t resume on the project Monday, there is a risk that interfaces will not be ready for UAT
Aug. 14th , 2024
Planned activities
Confirm Coffre-Fort selection process (criteria / teams) Work on detailed PT resource capacity planning Progress on Process mapping Impact Analysis Updated Change plan by role in progress Finalize WFM SIT with DO/DATA (until mid-sept.)
Watch Items
PT: Post Go-Live support model for PTWE-FR PT: Coffre-Fort Selection (Critical Path) PT: CGD: Finalize BPO PT: Train backfill
Go-Live : [Go live date]
Next 4 weeks milestones | Baseline Date | Current Date | STATUS
Impact Analysis Completed High-Level Change Plan per Role Completed Comm Material for changes and impacts Created SIT Completed UAT DIL Process Documented & Validated UAT DIL Testing Completed Sample Parallel Testing Completed Full Parallel Testing Completed Go-Live Date | 30/08/2024 30/08/2024 30/08/2024 30/08/2024 13/09/2024 18/10/2024 23/09/2024 22/10/2024 02/12/2024 | 30/08/2024 30/08/2024 30/08/2024 30/08/2024 13/09/2024 18/10/2024 23/09/2024 22/10/2024 02/12/2024 | In progress In progress In progress In progress In progress